SENAct Project/Erasmus+

2024-2-EL01-KA210-ADU-000286103-”Seniors in Action”

Quality Assurance Plan for the SENACT Project

1. QA Objectives

The overarching quality goal is to ensure all outputs are highly user-centric and successfully mitigate the identified barriers to digital inclusion.

| Objective | Rationale (Based on Needs Analysis) |
| --- | --- |
| I. Output Quality | To ensure all educational materials (Handbook, Multimedia/VR lessons) are directly relevant and appropriate for seniors (60+/65+) in both Domokos and Lisbon. |
| II. Usability & Accessibility | To ensure materials effectively address the critical psychological barriers (low confidence, fear of mistakes). Must consider physical/cognitive challenges (e.g., visual limitations, motor difficulties) identified in the Lisbon focus groups. |
| III. Implementation Quality | To ensure the "Seniors in Action" local training sessions are delivered consistently and effectively across both municipalities. |
| IV. Partnership Consistency | To maintain clear communication, timely delivery of tasks, and financial transparency across all three partners: Municipality of Domokos (Coordinator), Municipality of Lisbon, and LabSTEM. |

2. QA Roles and Monitoring Mechanisms

| Area | Responsibility | Mechanism/Tool |
| --- | --- | --- |
| Overall Coordination | Municipality of Domokos (Coordinator) | Monthly virtual coordination meetings and minutes. |
| Pedagogical/Technical | LabSTEM (Educational Technology Partner) | Review and validation of the Handbook and Multimedia/VR material drafts. |
| Target Group Validation | Municipality of Lisbon & Municipality of Domokos (Local Authorities) | Local testing, feedback collection from a sample of seniors, and internal partner sign-off before final publication/roll-out. |
| Progress Evaluation | Coordinator | Activity progress tracking against the proposed timetable and milestones. |

3. Quality Checks for Key Project Activities (Deliverables)

The QA process involves specific checks for each tangible intellectual output, ensuring it aligns with the data from the Needs Analysis (Activity 2).

| Activity/Deliverable | Quality Criteria | Verification Method (QA Check) |
| --- | --- | --- |
| Activity 3: Illustrated Handbook | Relevance: Content must cover high-interest topics: Video calling (58.6%), messaging/email (44.3%), and safety/banking etc (as stated in the proposal). Format: Must use illustrations and "big letters" suitable for older adults. Language: Must be translated accurately into English, Greek, and Portuguese. | Draft Review: LabSTEM and the Municipality of Lisbon review the initial draft against a checklist of topics from the Needs Analysis. Pilot Test: A sample of seniors reviews the physical format and readability for accessibility. Translation Check: Local partners review the native language versions for cultural and linguistic accuracy. |
| Activity 4: Multimedia/VR Lessons | Pedagogy: Lessons must build self-efficacy and reduce fear of technology. Technical: VR experience must be non-intimidating and easily transferred using freeware tools (e.g., cospaces.io). | Expert Vetting: LabSTEM educators internally test the VR content for ease of use and pedagogical soundness. Trainer Feedback: Trainers attending the LTTA (Activity 5) test and validate the VR material before it reaches the final target group. |
| Activity 5: Teaching the Teachers (LTTA) | Capacity Building: Trainers must be fully prepared to teach the material. Standardization: All trainers must deliver content consistently. | Workshop Evaluation: Participants complete an immediate feedback form (Qualitative) on the quality of the training, their confidence levels, and the clarity of the material. Post-Workshop Assessment: Trainers demonstrate their ability to use the VR technology and teach a specific lesson from the handbook. |
| Activity 6: Seniors in Action (Local Training) | Impact: The training must effectively engage seniors (aim: 15-20 seniors per municipality). Methodology: Emphasis must be on practical application and addressing the preference for human-mediated support. | Pre/Post-Course Survey: Seniors take a brief confidence/literacy questionnaire at the start and end of the 8 bi-monthly lessons to measure impact on self-efficacy. Observation: Designated partner staff (e.g., from the Municipality) observe a minimum of two lessons in each city to ensure adherence to the practice-heavy, 3-hour lesson plan. |